## Cover sheet
PROCUREMENT METHODS AND PRIOR REVIEW THRESHOLDS
(a) Goods/Works:
All ICB contracts for Goods and Works;
First two NCB contracts for Goods and First two NCB contracts for Works irrespective of the cost of the contract;
First Shopping contract for Goods and First Shopping contract for Works.
b) Consultants services
FIRMS:
All contracts with consulting firms estimated to cost US$300,000 or more;
First contract with consulting firms selected on the basis of Consultants Qualifications (CQ)
Individual Consultant
All contracts with individual consultants estimated to US$50,000 or more
All contracts with PIU staff irrespective of the cost of the contract;
General:
- The Terms of Reference for all consultant contracts with consulting firms and individual consultants irrespective of their costs;
Short lists comprising entirely national consultants shall be for assignments below USD 300,000;
Procurement method threshold
ICB | NCB | SHOPPING
$ USD | $ USD | $ USD
Goods Works | Goods Works | Goods Works
≥1.000.000 ≥ 5.000.000 | < 1.000.000 <5.000.000 | ≤ 100.000 ≤ 200.000
Prior review threshold
ICB | NCB | CONSULTANTS
$ USD | $ USD | $ USD
Goods Works | Goods Works | Firms Individual*
All All | First 2& >2.000.000;First 2&>10.000.000 | >1.000.000 > 300.000
*Individual Consultant Prior Review only under exceptional circumstances

## Consultant service
Ref No | Plan vs./ Actual | BEEP- Energy efficiency Project in Federation B&H October, 2014 | Name of Assignment/Contract | Category | Note #
[6 empty] | Selection Method | Review by Bank Prior / Post | Adverti- sement for EOI Date | Days Interval | Reception of expression of interest | Days Interval | Short Listing and RFP ready | Days Interval | No Objection Date | Days Interval | Invitation for RFP Date | Days Interval | Proposal Submission Date | Days Interval | Technical Evaluation Date | Days Interval | No Objection + PSC Date | Days Interval | Final Evaluation Date | Days Interval | No Objection Date to sign contract | Days Interval | Contract Signature Date | Days Interval | Start Date | Days Execution | Comple- tion Date
|  | A | B |  |  | D | E | F | [19 empty] | H |  | I |  | J
Consulting firms
COMPONENT 1
Combined Services for Clinics and chosen Schools
| P | Package 1: University Clinical Center Sarajevo Ortopedic and Traumatology; Surgery Clinic in Tuzla; Psychiatric Hospital Mostar | Detailed Energy Audit, TME before, Design, Audit of Design
A
BEEP-P143580-CQ-02-CS-15-FBIH | P |  | Supervision, TME after, Energy Labelling | CS |  | CQ | Prior | 2015-05-10 | 14 | 2015-05-24 | 8 | 2015-06-01 | 7 | 2015-06-08 | 0 | 2015-06-08 | 10 | 2015-06-18 | 4 | 2015-06-22 | 0 | 2015-06-22 | 0 | 2015-06-22 | 7 | 2015-06-29 | 170 | 2015-12-16 | 0 | 2015-12-16 | 300 | 2016-10-11
| A | [6 empty] | 2015-05-10 | 14 | 2015-05-24 | 8 | 2015-06-01 | 7 | 2015-06-08 | 0 | 2015-06-08 | 10 | 2015-06-18 | 4 | 2015-06-22 | 0 | 2015-06-22 | 0 | 2015-06-22 | 7 | 2015-06-29 | 170 | 2015-12-17 | 0 | 2016-02-01 | 408 | 2017-03-15
BEEP-P143580-CQ-04-CS-15-FBIH | P | Package 2 (10+3=13 objects) Ze-Do, Una-Sana, HNK Elementary School Ivana fra Frane Jukica Sivsa Usora; Elementary School 21. mart Doboj Jug; Gimnasium Rizah Odzeckic Zavidovici; Elementary School "Gazi Ferhad-beg" Tesanj; Secondary Mutual School Zepce; Hospital Bihać; Elementary school Bosanska Otoka; I Secondary school Dr. Husein Džanić & II secondary school, Gymnasium; Elementary school Stijena Cazin; I & II Secondary school Cazin; Elementary School Fra Didaka Buntića Čitluk; Secondary School Čapljina; Elementary School Crnići Stolac (allocated) | Combined Services (Design, technical monitoring (before and after), works supervision) | CS |  | CQ | Prior | 2015-12-01 | 14 | 2015-12-15 | 8 | 2015-12-23 | 7 | 2015-12-30 | 0 | 2015-12-30 | 10 | 2016-01-09 | 4 | 2016-01-13 | 0 | 2016-01-13 | 0 | 2016-01-13 | 7 | 2016-01-20 | 2 | 2016-01-22 | 0 | 2016-01-22 | 450 | 2017-04-16
| A | [6 empty] | 2015-12-02 | 13 | 2015-12-15 | 24 | 2016-01-08 |  | 22.01.2016. |  | 22.01.2016. |  | 29.01.2016. | 10 | 05.02.2016. | 0 | 05.02.2016. | 0 | 05.02.2016. |  | 2016-02-12 |  | 2016-02-15 |  | 2016-02-15 |  | 2018-06-30
| P | Package 3 (12+4=16 objects Ze-Do, Sarajevo, HNK) Secondary Mutual School Stjepana Radica Usora; Elementary School Safvet-beg Basagic Visoko; Elementary School Kulin Ban Visoko; Elementary School "Musa Cazim Catic" Zenica; Elementary School "Hamdija Kresevljakovic" Kakanj; Elementary School 15. April Kakanj; Elementary School „Mula Mustafa Baseskija“ Visoko; First elementary school Zavidovici; Hospital Tesanj; Elementary School „Zahid Barucija; Elementary School „Hasim Spahic“; Elementary School „Srednje“ Ilijas; Secondary School Juraja Dalmatinca Mostar; Hospital Jablanica; Secondary School Konjic; IV Elementary School Mostar (allocated) | Detailed Energy Audit, TME before, Design completed for „Mula Mustafa Baseskija“ Visoko
A
BEEP-P143580-CQ-05-CS-15-FBIH |  |  | Combined Services (Design, technical monitoring (before and after), works supervision) | CS |  | CQ | Prior | 2015-12-01 | 14 | 2015-12-15 | 8 | 2015-12-23 | 7 | 2015-12-30 | 0 | 2015-12-30 | 10 | 2016-01-09 | 4 | 2016-01-13 | 0 | 2016-01-13 | 0 | 2016-01-13 | 7 | 2016-01-20 | 2 | 2016-01-22 | 0 | 2016-01-22 | 450 | 2017-04-16
| A | [6 empty] | 2015-12-02 | 13 | 2015-12-15 |  | 08.01.2016. |  | 22.01.2016. |  | 22.01.2016. |  | 29.01.2016. |  | 05.02.2016. | 0 | 05.02.2016. | 0 | 05.02.2016. |  | 2016-02-12 |  | 2016-02-15 |  | 2016-02-15 |  | 2018-06-30
BEEP-P143580-CQ-01-CS-15-FBIH | P | Package 2, 3 (allocated) | Audit of Design | CS |  | CQ | Post | 2015-12-01 | 14 | 2015-12-15 | 8 | 2015-12-23 | 0 | 2015-12-23 | 0 | 2015-12-23 | 10 | 2016-01-02 | 0 | 2016-01-02 | 7 | 2016-01-09 | 0 | 2016-01-09 | 0 | 2016-01-09 | 2 | 2016-01-11 | 0 | 2016-01-11 | 65 | 2016-03-16
| A | [6 empty] | 2015-12-02 | 13 | 2015-12-15 |  | 14.01.2016. |  | - |  | 20.01.2016. |  | 27.01.2016. |  | 01.02.2016. | 0 | 01.02.2016. | 0 | 01.02.2016. | 0 | - | 0 | 2016-02-08 |  | 2016-02-15 | 90 | 2016-05-15
BEEP-P143580-CQ-06-CS-16-FBIH | P | Package 4 (2017. buldings) (allocated) | Combined Services (Design for 18 objects, Technical monitoring before and after for 19 objects, Works Supervision for 13 Objects) | CS |  | CQ | Post | 2017-01-15 | 14 | 2017-01-29 | 2 | 2017-01-31 | 3 | N/A | 0 | 2017-02-03 | 7 | 2017-02-10 | 3 | 2017-02-13 | 0 | N/A | 2 | 2017-02-15 | 0 | N/A | 0 | 2017-02-15 | 0 | 2017-02-15 | 410 | 2018-04-01
| A | [6 empty] | 2017-01-17 | 15 | 2017-02-01 |  | 2017-02-15 | 0 | N/A | 0 | 2017-02-15 | 7 | 2017-02-22 |  | 2017-02-24 | 0 | N/A | 0 | 2017-02-24 |  | N/A |  | 2017-03-02 | 0 | 2017-03-02 |  | 2018-06-30
BEEP-P143580-CQ-07-CS-16-FBIH | P | Package 5 (2017. buildings) (allocated) | Combined Services (Works Supervision for 5 federal level objects + 1 object for Piloting, Audit of design for 19 objects) | CS |  | CQ | Post | 2017-01-15 | 14 | 2017-01-29 | 2 | 2017-01-31 | 3 | N/A | 0 | 2017-02-03 | 7 | 2017-02-10 | 3 | 2017-02-13 | 0 | N/A | 0 | 2017-02-13 | 2 | N/A | 2 | 2017-02-15 | 0 | 2017-02-15 | 410 | 2018-04-01
| A | [6 empty] | 2017-01-17 | 15 | 2017-02-01 |  | 2017-02-15 | 0 | N/A | 0 | 2017-02-15 | 7 | 2017-02-22 |  | 2017-02-24 | 0 | N/A | 0 | 2017-02-24 |  | N/A |  | 2017-03-06 | 0 | 2017-03-06 |  | 2018-06-30
F. Detailed energy audits
BEEP-P143580-CQ-11-CS-16-FBIH | P | 72 detailed energy audits (to be allocated) - 2017. buldings | Consultant engineering service | CS |  | CQ | Post | 2016-02-01 | 14 | 2016-02-15 | 8 | 2016-02-23 | 7 | N/A | 0 | 2016-02-23 | 10 | 2016-03-04 | 4 | 2016-03-08 | 0 | N/A | 0 | 2016-03-08 | 7 | N/A | 2 | 2016-03-10 | 0 | 2016-03-10 | 90 | 2016-06-08
| A | [6 empty] | 2016-04-19 | 14 | 2016-05-04 |  | 2016-05-06 |  | N/A |  | 2016-05-09 | 7 | 2016-05-16 |  | 2016-05-19 | 0 | N/A | 0 | 2016-05-24 | 0 | N/A | 0 | 2016-06-09 | 0 | 2016-06-09 | 90 | 2016-09-07
BEEP-P143580-CQ-18-CS-16-FBIH | P | 30 detailed energy audits (to be allocated) - 2017. buldings | Consultant engineering service | CS |  | CQ | Post | 2016-05-25 | 14 | 2016-06-08 | 8 | 2016-06-16 | 7 | N/A | 0 | 2016-06-16 | 10 | 2016-06-26 | 4 | 2016-06-30 | 0 | N/A | 0 | 2016-06-30 | 7 | N/A | 2 | 2016-07-02 | 0 | 2016-07-02 | 45 | 2016-08-16
| A | [6 empty] | 2016-07-04 | 14 | 2016-07-18 |  | 2016-07-25 |  | N/A |  | 2016-08-03 | 7 | 2016-08-10 | 1 | 2016-08-11 | 0 | N/A | 0 | 2016-08-12 | 0 | N/A | 0 | 2016-08-25 |  | 2016-08-25 | 60 | 2016-10-24
G. Social monitoring and evaluation
BEEP-P143580-CQ-12-CS-15-FBIH | P | Social monitoring and evaluation -(IA) (alocated) | Consultant services | CS |  | CQ | Post | 2015-12-20 | 14 | 2016-01-03 | 8 | 2016-01-11 | 7 | N/A | 0 | 2016-01-11 | 10 | 2016-01-21 | 4 | 2016-01-25 | 0 | N/A | 0 | 2016-01-25 | 7 | N/A | 2 | 2016-01-27 | 0 | 2016-01-27 | 790 | 2018-03-27
| A | [6 empty] | 11.01.2016. |  | 25.01.2016. |  | 2016-02-01 |  | - |  | 2016-02-09 | 7 | 2016-02-16 | 1 | 2016-02-17 | 0 | N/A | 0 | 2016-03-28 |  | - |  | 2016-04-05 | 0 | 2016-04-05 |  | 2018-06-01
Total Estimate cost
Subtotal Allocated
To be allocated
TOTAL COMPONENT 1
COMPONENT 2
Sub-Component A: Support for scalable financing mechanisms
Consultant firms
BEEP-P143580-IC-13-CS-16-FBIH-I | P | Senior International Energy Efficiency Consultant for the Development of the Issue and Options Study on Scalable Financing Mechanisms | Consultant service | CS |  | IC | Post | 2016-12-15 | 14 | 2016-12-29 | 8 | 2017-01-06 | 7 | 2017-01-13 | 0 | 2017-01-13 | 10 | 2017-01-23 | 4 | 2017-01-27 | 0 | 2017-01-27 | 0 | 2017-01-27 | 7 | 2017-02-03 | 2 | 2017-02-10 | 0 | 2017-02-10 |  | 2017-02-10
| A | [6 empty] | 2017-02-20 | 14 | 2017-03-06 | 8 | 2017-03-14 | 7 | 2017-03-21 | 0 | 2017-03-21 | 10 | 2017-03-31 | 4 | 2017-04-04 | 0 | 2017-04-04 | 0 | 2017-04-04 | 7 | 2017-04-11 | 2 | 2017-08-11 |  | 2017-08-31 | 48 | 2018-04-30
BEEP-P143580-IC-13-CS-16-FBIH-II |  | Financial Expert for the Development of the Issue and Options Study on Scalable Financing Mechanisms | Consultant service | CS |  | IC | Post | 2016-12-15 | 14 | 2016-12-29 | 8 | 2017-01-06 | 7 | 2017-01-13 | 0 | 2017-01-13 | 10 | 2017-01-23 | 4 | 2017-01-27 | 0 | 2017-01-27 | 0 | 2017-01-27 | 7 | 2017-02-03 | 2 | 2017-02-10 | 0 | 2017-02-10 |  | 2017-02-10
| A | [6 empty] | 2017-02-20 | 14 | 2017-03-06 | 8 | 2017-03-14 | 7 | 2017-03-21 | 0 | 2017-03-21 | 10 | 2017-03-31 | 4 | 2017-04-04 | 0 | 2017-04-04 | 0 | 2017-04-04 | 7 | 2017-04-11 | 2 | 2017-08-22 |  | 2017-08-31 | 50 | 2018-04-30
BEEP-P143580-IC-13-CS-16-FBIH-III |  | Policy/Regulatory Expert for the Development of the Issue and Options Study on Scalable Financing Mechanisms | Consultant service | CS |  | IC | Post | 2016-12-15 | 14 | 2016-12-29 | 8 | 2017-01-06 | 7 | 2017-01-13 | 0 | 2017-01-13 | 10 | 2017-01-23 | 4 | 2017-01-27 | 0 | 2017-01-27 | 0 | 2017-01-27 | 7 | 2017-02-03 | 2 | 2017-02-10 | 0 | 2017-02-10 |  | 2017-02-10
| A | [6 empty] | 2017-02-20 | 14 | 2017-03-06 | 8 | 2017-03-14 | 7 | 2017-03-21 | 0 | 2017-03-21 | 10 | 2017-03-31 | 4 | 2017-04-04 | 0 | 2017-04-04 | 0 | 2017-04-04 | 7 | 2017-04-11 | 2 | 2017-08-22 |  | 2017-08-31 | 65 | 2018-04-30
BEEP-P143580-IC-13-CS-16-FBIH-IV |  | Technical Expert for the Development of the Issue and Options Study on Scalable Financing Mechanisms | Consultant service | CS |  | IC | Post | 2016-12-15 | 14 | 2016-12-29 | 8 | 2017-01-06 | 7 | 2017-01-13 | 0 | 2017-01-13 | 10 | 2017-01-23 | 4 | 2017-01-27 | 0 | 2017-01-27 | 0 | 2017-01-27 | 7 | 2017-02-03 | 2 | 2017-02-10 | 0 | 2017-02-10 |  | 2017-02-10
| A | [6 empty] | 2017-02-20 | 14 | 2017-03-06 | 8 | 2017-03-14 | 7 | 2017-03-21 | 0 | 2017-03-21 | 10 | 2017-03-31 | 4 | 2017-04-04 | 0 | 2017-04-04 | 0 | 2017-04-04 | 7 | 2017-04-11 | 2 | 2017-08-22 |  | 2017-08-31 | 40 | 2018-04-30
Subtotal Allocated A
To be allocated A
Subtotal Subcomponent A
Sub-Component B: Capacity building
BEEP-P143580-CQ-14-CS-16-FBIH | P | Training Municipality energy management-certification | Consultant service | CS |  | CQ | Post | 2016-12-01 | 14 | 2016-12-15 | 8 | 2016-12-23 | 7 | 2016-12-30 | 0 | 2016-12-30 | 10 | 2017-01-09 | 4 | 2017-01-13 | 0 | 2017-01-13 | 0 | 2017-01-13 | 7 | 2017-01-20 | 2 | 2017-01-27 | 0 | 2017-01-27 | 450 | 2018-04-22
| A | [6 empty] | 2017-01-04 | 14 | 2017-01-18 |  | 2017-01-27 | 0 | 2017-01-27 | 0 | 2017-01-30 | 7 | 2017-02-06 | 1 | 2017-02-07 | 0 | 2017-02-07 | 0 | 2017-02-07 | 0 | 2017-02-07 | 0 | 2017-03-02 |  | 2017-03-02 |  | 2018-04-30
BEEP-P143580-CQ-15-CS-16-FBIH | P | "Communications, awareness raising and outreach". | Consultant service | CS | multi | CQ | Post | 2016-01-15 | 14 | 2016-01-29 | 8 | 2016-02-06 | 7 | 2016-02-13 | 0 | 2016-02-13 | 10 | 2016-02-23 | 4 | 2016-02-27 | 0 | 2016-02-27 | 0 | 2016-02-27 | 7 | 2016-03-05 | 2 | 2016-03-12 | 0 | 2016-03-12 | 811 | 2018-06-01
| A | [6 empty] | 13.01.2016. |  | 26.01.2016. |  | 2016-02-01 |  | - |  | 2016-02-09 | 7 | 2016-02-16 |  | 2016-02-17 |  | - |  | 2016-02-19 |  | - |  | 2016-02-22 |  | 2016-02-22 | 830 | 2018-06-01
BEEP-P143580-CQ-16-CS-16-FBIH | P | Promotion of EE results | Consultant service | CS | multi | CQ | Post | 2016-02-20 | 14 | 2016-03-05 | 8 | 2016-03-13 | 7 | 2016-03-20 | 0 | 2016-03-20 | 10 | 2016-03-30 | 4 | 2016-04-03 | 0 | 2016-04-03 | 0 | 2016-04-03 | 7 | 2016-04-10 | 2 | 2016-04-17 | 0 | 2016-04-17 | 775 | 2018-06-01
| A | [6 empty] | 2016-02-22 | 14 | 2016-03-07 |  | 2016-03-20 |  | - |  | 2016-03-20 |  | 2016-03-24 |  | 2016-03-25 |  | - |  | 2016-03-29 | 0 | - | 0 | 2016-04-05 |  | 2016-04-05 |  | 2018-06-01
BEEP-P143580-CQ-17-CS-16-FBIH | P | Other technical assistance and Trainings | Consultant service | CS | multi | CQ | Post | 2017-01-20 | 14 | 2017-02-03 | 8 | 2017-02-11 | 7 | 2017-02-18 | 0 | 2017-02-18 | 10 | 2017-02-28 | 4 | 2017-03-04 | 0 | 2017-03-04 | 0 | 2017-03-04 | 7 | 2017-03-11 | 2 | 2017-03-18 | 0 | 2017-03-18 | 410 | 2018-05-02
A
Subtotal Allocated B
To be allocated B
Subtotal Subcomponent B
Total A+B - allocated
To be allocated
TOTAL COMPONENT 2
COMPONENT 3
Project management
BEEP-P143580-IC-01-CS-14-FBIH |  | Project Coordinator | Consultant service | CS |  | IC | Prior | 2014-02-21 | 7 | 2014-02-28 |  | 2014-03-03 |  | 2014-03-12 | 1 | 2014-03-13 | 1 | 2014-03-14 | 0 | 2014-03-14 | 0 | 2014-03-12 | 0 | 2014-03-17 |  | 2015-11-28 |  | 2015-12-16 | 0 | 2015-12-16 | 167 | 2016-05-31
[6 empty] | IC | Post | [20 empty] | 2016-06-01 | 0 | 2016-06-01 | 759 | 2018-06-30
BEEP-P143580-IC-02-CS-14-FBIH |  | Procurement specialist | Consultant service | CS |  | IC | Prior | 2014-02-21 | 7 | 2014-02-28 |  | 2014-03-03 |  | 2014-03-12 | 1 | 2014-03-13 | 1 | 2014-03-14 | 0 | 2014-03-14 | 0 | 2014-03-12 | 0 | 2014-03-17 |  | 2015-11-28 |  | 2015-12-16 | 0 | 2015-12-16 | 167 | 2016-05-31
[7 empty] | Post | [20 empty] | 2016-06-01 | 0 | 2016-06-01 | 759 | 2018-06-30
BEEP-P143580-IC-06-CS-14-FBIH |  | Financial specialist | Consultant service | CS |  | IC | Prior | 2015-08-26 | 18 | 2015-09-13 |  | 2015-10-20 |  | 2015-11-17 | 1 | 2015-11-18 | 7 | 2015-11-25 | 1 | 2015-11-26 | 3 | 2015-11-29 | 1 | 2015-11-30 |  | 2016-01-07 |  | 2015-12-16 | 0 | 2015-12-16 | 167 | 2016-05-31
[7 empty] | Post | [20 empty] | 2016-06-01 | 0 | 2016-06-01 | 328 | 2017-04-25
[7 empty] | Prior |  |  |  |  | 2017-04-21 |  | 2017-04-21 | 1 | 2017-04-22 | 1 | 2017-04-23 | 0 | 2017-04-26 | 0 | 2017-05-09 | 0 | 2017-05-09 |  | 2017-05-09 |  | 2017-05-11 | 0 | 2017-05-11 | 415 | 2018-06-30
BEEP-P143580-IC-04-05-CS-14-FBIH |  | Senior building expersts | Consultant service | CS | multi | IC | Prior | 2014-10-22 | 14 | 2014-11-05 |  | 2014-11-21 |  | 2015-01-26 |  | 2015-01-26 |  | 2015-01-26 |  | 2015-01-26 |  | 2015-01-26 |  | 2015-01-26 |  | 2015-11-28 |  | 2015-12-16 | 0 | 2015-12-16 | 167 | 2016-05-31
[7 empty] | Post | [20 empty] | 2016-06-01 | 0 | 2016-06-01 | 759 | 2018-06-30
BEEP-P143580-IC-03-CS-14-FBIH |  | Administrative assistant | Consultant service | CS |  | IC | Prior | 2014-10-22 | 14 | 2014-11-05 | 7 | 2014-11-21 |  | 2015-01-26 |  | 2015-01-26 |  | 2015-01-26 |  | 2015-01-26 |  | 2015-01-26 |  | 2015-01-26 |  | 2015-12-22 |  | 2015-12-16 | 0 | 2015-12-16 | 167 | 2016-05-31
[7 empty] | Post | [20 empty] | 2016-06-01 | 0 | 2016-06-01 | 759 | 2018-06-30
BEEP-P143580-IC-44-CS-16-FBIH |  | Temporary Technical Expert (for HNK Canton) | Consultant service | CS |  | IC | Post | 2016-08-08 | 7 | 2016-08-15 | 3 | 2016-08-18 | 3 | 2016-08-21 | 1 | 2016-08-22 | 0 | 2016-08-22 | 0 | 2016-08-22 | 0 | 2016-08-22 | 1 | 2016-08-23 | 0 | 2016-08-23 | 0 | 2016-08-23 | 0 | 2016-08-23 | 120 | 2016-12-21
[6 empty] | IC | Post | 2016-08-10 | 5 | 2016-08-15 |  | 2016-08-16 |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 2016-08-16 |  | N/A |  | 2016-08-23 |  | 2016-08-23 | 122 | 2016-12-23
BEEP-P143580-IC-45-CS-16-FBIH |  | Temporary Technical Expert (for UNA-SANA Canton) | Consultant service | CS |  | IC | Post | 2016-09-08 | 7 | 2016-09-15 | 3 | 2016-09-18 | 3 | 2016-09-21 | 1 | 2016-09-22 | 0 | 2016-09-22 | 0 | 2016-09-22 | 0 | 2016-09-22 | 1 | 2016-09-23 | 0 | 2016-09-23 | 0 | 2016-09-23 | 0 | 2016-09-23 | 120 | 2017-01-21
BEEP-P143580-SSS-28-S-15-FBIH | P | Financial Software for World Bank Project | software |  |  | SSS | Prior | 2015-09-14 | 7 | 2015-09-21 | 7 | 2015-09-28 | 7 | 2015-10-05 | 7 | 2015-10-12 | 7 | 2015-10-19 | 3 | 2015-10-22 | 1 | 2015-10-23 | 1 | 2015-10-23 | 5 | 2015-10-28 | 48 | 2015-12-15 | 0 | 2015-12-16 | 30 | 2016-01-15
| A | [6 empty] | 2015-10-14 | 0 | 2015-10-14 | 0 | 2015-10-14 | 0 | 2015-10-14 | 0 | 2015-10-14 | 1 | 2015-10-15 | 11 | 2015-10-26 | 0 | 2015-10-26 | 0 | 2015-10-26 | 0 | 2015-10-26 | 51 | 2015-12-16 |  | 2015-12-16 | 30 | 2016-01-15
Incremental operating costs
A
Annual financial audit
A
Total component 3 - allocated
|  |  | To be allocated | [26 empty] | 2014-09-01 | 1398 | 2018-06-30
TOTAL COMPONENT 3
GRAND TOTAL CONSULTANT SERVICES
Formulas:
Reception of expression of interest = [Adverti- sement for EOI Date]+[Days Interval]
Reception of expression of interest = [Adverti- sement for EOI Date]+[Days Interval]+1
Short Listing and RFP ready = [Reception of expression of interest]+[Days Interval]
No Objection Date = [Short Listing and RFP ready]+[Days Interval]
Invitation for RFP Date = [No Objection Date]+[Days Interval]
Invitation for RFP Date = [Short Listing and RFP ready]+[Days Interval]
Proposal Submission Date = [Invitation for RFP Date]+[Days Interval]
Technical Evaluation Date = [Proposal Submission Date]+[Days Interval]
No Objection + PSC Date = [Technical Evaluation Date]+[Days Interval]
Final Evaluation Date = [No Objection + PSC Date]+[Days Interval]
Final Evaluation Date = [Technical Evaluation Date]+[Days Interval]
No Objection Date to sign contract = [Final Evaluation Date]+[Days Interval]
Contract Signature Date = [No Objection Date to sign contract]+[Days Interval]
Contract Signature Date = [No Objection Date to sign contract]+[Days Interval]+1
Start Date = [Contract Signature Date]+[Days Interval]
Start Date = [Contract Signature Date]+30+16
Comple- tion Date = [Start Date]+[Days Execution]

## Works and goods
Ref no | Plan vs./ Actual | BEEP- Energy efficiency Project in Federation B&H December, 2013 | Name of Assignment/Contract | Category | Note # | Selection Method | Review by Bank Prior / Post | Submis- sion/ Readiness Date | Days Interval | No Objection Date | Days Interval | Invita- tion Date | Days Interval | Bid- Opening Date | Days Interval | Evalu- ation & Recomm. | Days Interval | No Objection Date + PSC | Days Interval | Contract Award Date | Days Interval | contarct Siganture date | Days Interval | Start Date | Days Execution | Comple- tion Date | Days Execution
CLINICS
BEEP-P143580-NCB-29-W-15-FBIH |  | PACKAGE 1 University Clinical Center Sarajevo Ortopedic and Traumatology | Works on reconstruction of Clinics | W |  | NCB | Prior | 2015-05-01 | 7 | 2015-05-08 | 3 | 2015-05-11 | 28 | 2015-06-08 | 14 | 2015-06-22 | 4 | 2015-06-26 | 5 | 2015-07-01 | 16 | 2015-07-17 | 0 | 2015-07-17 | 123 | 2015-11-17 | 1
| A | [6 empty] | 29.04.2015. |  | 03.05.2015. |  | 13.05.2015. |  | 09.06.2015. |  | 30.06.2015. |  | 08.07.2015. |  | 18.12.2015. |  | 18.12.2015. |  | 02.03.2016. |  | 30.06.2016.
BEEP-P143580-NCB-30-W-15-FBIH |  | PACKAGE 2 LOT 1 - Psychiatric Hospital Mostar | Works on reconstruction of Clinics | W |  | NCB | Prior | 2015-05-20 | 7 | 2015-05-27 | 2 | 2015-05-29 | 28 | 2015-06-26 | 14 | 2015-07-10 | 7 | 2015-07-17 | 3 | 2015-07-20 | 11 | 2015-07-31 | 0 | 2015-07-31 | 114 | 2015-11-22 | 1
|  | PACKAGE 2 LOT 2 - Health Centre Tuzla - Surgery Clinic |  | W |  |  |  | 2015-05-20 | 7 | 2015-05-27 | 2 | 2015-05-29 | 28 | 2015-06-26 | 14 | 2015-07-10 | 7 | 2015-07-17 | 3 | 2015-07-20 | 11 | 2015-07-31 | 0 | 2015-07-31 | 121 | 2015-11-29 | 1
| A | [6 empty] | 14.05.2015. |  | 18.05.2015. |  | 2015-05-21 |  | 17.06.2015. |  | 08.08.2015. |  | 22.09.2015. |  | 18.12.2015. |  | 18.12.2015. |  | 01.02.2016. |  | 31.05.2016.
CANTONS 2016. buildings
BEEP-P143580-NCB-31-W-16-FBIH | P | PACKAGE 3 - 2016. buildings (3 buildings) (allocated) | Works on reconstruction of Sarajevo Canton | W | Estimated Cost is from Design | NCB | Post | 2016-04-18 | 0 | 2016-04-18 | 0 | 2016-04-18 | 21 | 2016-05-09 | 5 | 2016-05-14 | 5 | 2016-05-19 | 2 | 2016-05-21 | 30 | 2016-06-20 | 0 | 2016-06-20 | 90 | 2016-09-18 | 1
| A | [10 empty] | 2016-04-20 | 21 | 2016-05-12 |  | 2016-07-15 |  | N/A |  | 2016-07-15 |  | 2016-07-22 |  | 2016-08-01 | 90 | 2016-10-30
BEEP-P143580-NCB-32-W-16-FBIH | p | PACKAGE 4- 2016. buildings (5 buildings) (allocated) | Works on reconstruction of UNA-SANA Canton | W | Estimated Cost is from Design | NCB | Post | 2016-04-18 | 0 | 2016-04-18 | 0 | 2016-04-18 | 21 | 2016-05-09 | 5 | 2016-05-14 | 5 | 2016-05-19 | 2 | 2016-05-21 | 30 | 2016-06-20 | 0 | 2016-06-20 | 90 | 2016-09-18 | 1
| A | [10 empty] | 2016-04-21 | 21 | 2016-05-13 |  | 2016-07-13 |  | N/A |  | 2016-07-13 |  | 2016-07-22
BEEP-P143580-NCB-33-W-16-FBIH | P | PACKAGE 5 - 2016. buildings (5 buildings) (allocated) | Works on reconstruction of ZE-DO Canton | W | Estimated Cost is from Design | NCB | Post | 2016-04-18 | 0 | 2016-04-18 | 0 | 2016-04-18 | 21 | 2016-05-09 | 5 | 2016-05-14 | 5 | 2016-05-19 | 2 | 2016-05-21 | 30 | 2016-06-20 | 0 | 2016-06-20 | 90 | 2016-09-18 | 1
| A | [10 empty] | 2016-04-29 | 21 | 2016-05-20 |  | 2016-07-13 |  | N/A |  | 2016-07-13 |  | 2016-07-22 |  | 2016-08-08 | 114 | 2016-11-30
BEEP-P143580-NCB-34-W-16-FBIH | P | PACKAGE 6 - LOT 1 - 2016. buildings (2 buildings) (allocated) | Works on reconstruction of HNK Canton | W | Estimated Cost is from DEA | NCB | Post | 2016-04-25 | 0 | 2016-04-25 | 0 | 2016-04-25 | 21 | 2016-05-16 | 5 | 2016-05-21 | 5 | 2016-05-26 | 2 | 2016-05-28 | 30 | 2016-06-27 | 0 | 2016-06-27 | 90 | 2016-09-25 | 1
|  | PACKAGE 6 - LOT 2 - 2016. buildings (5 buildings) (allocated) |  | W | Estimated Cost is from DEA | NCB | Post | 2016-04-25 | 0 | 2016-04-25 | 0 | 2016-04-25 | 21 | 2016-05-16 | 5 | 2016-05-21 | 5 | 2016-05-26 | 2 | 2016-05-28 | 30 | 2016-06-27 | 0 | 2016-06-27 | 90 | 2016-09-25 | 1
| A |  |  |  | LOT 1 | [6 empty] | 2016-05-27 | 21 | 2016-06-17 |  | 2016-07-14 |  | N/A |  | 2016-07-14 |  | 2016-07-25 |  | 2016-08-03 | 139 | 2016-12-20
[5 empty] | LOT 2 | [6 empty] | 2016-05-27 | 21 | 2016-06-17 |  | 2016-07-14 |  | N/A |  | 2016-07-14 |  | 2016-07-25 |  | 2016-08-08 | 145 | 2016-12-31
TOTAL 2016. BUILDINGS
CANTONS 2017. buildings
BEEP-P143580-NCB-35-W-16-FBIH | P | PACKAGE 7 2017. buildings (9 buildings) (allocated) | Works on reconstruction of 4 objects in HNK Canton | W |  | NCB | Post | 2017-07-01 | 0 | 2017-07-01 | 0 | 2017-07-01 | 21 | 2017-07-22 | 5 | 2017-07-27 | 14 | 2017-08-10 | 2 | 2017-08-12 | 30 | 2017-09-11 | 0 | 2017-09-11 | 120 | 2018-01-09 | 1
A
BEEP-P143580-NCB-36-W-16-FBIH | P | PACKAGE 8 2017. buildings (5 buildings) (allocated) | Works on reconstruction of 5 objects in ZE-DO Canton | W |  | NCB | Post | 2017-05-03 | 0 | 2017-05-03 | 0 | 2017-05-03 | 21 | 2017-05-24 | 5 | 2017-05-29 | 14 | 2017-06-12 | 2 | 2017-06-14 | 30 | 2017-07-14 | 0 | 2017-07-14 | 120 | 2017-11-11 | 1
| A | [10 empty] | 2017-05-15 | 21 | 2017-06-05 |  | 2017-07-10 |  | 2017-07-10 |  | 2017-07-28 |  | 2017-08-22 |  | 2017-08-23 | 120 | 2017-12-21
BEEP-P143580-NCB-37-W-16-FBIH | P | PACKAGE 9 2017. buildings (6 buildings) (allocated) | Works on reconstruction of 1 object in Canton Sarajevo & 5 federal level objects | W |  | NCB | Post | 2017-06-15 | 0 | 2017-06-15 | 0 | 2017-06-15 | 21 | 2017-07-06 | 5 | 2017-07-11 | 14 | 2017-07-25 | 2 | 2017-07-27 | 30 | 2017-08-26 | 0 | 2017-08-26 | 120 | 2017-12-24 | 1
| A | [10 empty] | 2017-06-07 | 21 | 2017-06-28 |  | 2017-07-17 |  | 2017-07-17 |  | 2017-07-28 |  | 2017-08-22 |  | 2017-08-23 | 120 | 2017-12-21
BEEP-P143580-NCB-38-W-16-FBIH | P | PACKAGE 10 2017. buildings (2 buildings) (allocated) | Works on reconstruction of 2 objects in Livanjski Canton | W |  | NCB | Post | 2017-05-03 | 0 | 2017-05-03 | 0 | 2017-05-03 | 21 | 2017-05-24 | 5 | 2017-05-29 | 14 | 2017-06-12 | 2 | 2017-06-14 | 30 | 2017-07-14 | 0 | 2017-07-14 | 120 | 2017-11-11 | 1
| A | [10 empty] | 2017-05-22 | 21 | 2017-06-12 |  | 2017-07-10 |  | 2017-07-10 |  | 2017-07-28 |  | 2017-08-22 |  | 2017-08-23 | 120 | 2017-12-21
BEEP-P143580-NCB-44-W-16-FBIH | P | PACKAGE 11 2017. buildings (1 building) (allocated) | Works on reconstruction of 1 object in Canton Sarajevo | W |  | NCB | Post | 2017-07-15 | 0 | 2017-07-15 | 0 | 2017-07-15 | 21 | 2017-08-05 | 5 | 2017-08-10 | 14 | 2017-08-24 | 2 | 2017-08-26 | 30 | 2017-09-25 | 0 | 2017-09-25 | 120 | 2018-01-23 | 1
| A | [10 empty] | 2017-08-17 | 21 | 2017-09-07
BEEP-P143580-NCB-45-W-16-FBIH |  | PACKAGE 12 2017. buildings (1 building) (allocated) | Works on reconstruction of 1 object in ZE-DO Canton | W |  | NCB | Post | 2017-06-27 | 0 | 2017-06-27 | 0 | 2017-06-27 | 21 | 2017-07-18 | 5 | 2017-07-23 | 14 | 2017-08-06 | 2 | 2017-08-08 | 30 | 2017-09-07 | 0 | 2017-09-07 | 90 | 2017-12-06
| A | [10 empty] | 2017-07-11 | 21 | 2017-08-01 |  | 2017-08-17 |  | 2017-08-17 |  | 2017-08-21 |  |  |  |  | 90
TOTAL 2017. BUILDINGS
Total works - Component 1 / Hospitals, Schools and Administrative buildings/
allocated
to be allocated
GOODS
BEEP-P143580-SH-39-G-16-FBIH |  | Purchasing and Instalation (Performance Monitoring System for measuring the temperature and humidity) (20+7=27 buildings) - 2016./2017. buldings (allocated) |  | G |  | SH | Post | 2016-02-05 | 2 | 2016-02-07 | 3 | 2016-02-10 | 14 | 2016-02-24 | 1 | 2016-02-25 | 3 | 2016-02-28 | 0 | 2016-02-28 | 0 | 2016-02-28 | 0 | 2016-02-28 | 20 | 2016-03-19 | 1
| A | [8 empty] | 25.01.2016. |  | 01.02.2016. |  | 2016-02-03 |  | 2016-02-03 |  | - |  | 2016-02-05 |  | 2016-02-08 |  | 2016-02-08 | 105 | 2016-05-23
BEEP-P143580-SH-40-G-16-FBIH |  | Purchasing and Instalation (Performance Monitoring System for measuring the heat energy usage) (20+7=27 buildings) - 2016./2017. buldings (allocated) |  | G |  | SH | Post | 2016-02-05 | 2 | 2016-02-07 | 3 | 2016-02-10 | 14 | 2016-02-24 | 1 | 2016-02-25 | 3 | 2016-02-28 | 0 | 2016-02-28 | 0 | 2016-02-28 | 0 | 2016-02-28 | 20 | 2016-03-19 | 1
| A | [8 empty] | 25.01.2016. |  | 01.02.2016. |  | 2016-02-03 |  | 2016-02-03 |  | - |  | 2016-02-05 |  | 2016-02-08 |  | 2016-02-08 | 105 | 2016-05-23
BEEP-P143580-SH-41-G-16-FBIH |  | Purchasing and Instalation (Performance Monitoring System for measuring the temperature and humidity) (for 19 buildings) - 2017. buldings (allocated) |  | G |  | SH | Post | 2017-01-15 | 0 | 2017-01-15 | 0 | 2017-01-15 | 7 | 2017-01-22 | 1 | 2017-01-23 | 3 | 2017-01-26 | 0 | 2017-01-26 | 0 | 2017-01-26 | 0 | 2017-01-26 | 30 | 2017-02-25 | 1
| A | [6 empty] | 2017-01-23 | 0 | 2017-01-23 | 0 | 2017-01-23 | 7 | 2017-01-30 | 2 | 2017-02-01 | 0 | 2017-02-01 | 0 | 2017-02-01 | 0 | 2017-02-16 | 0 | 2017-02-16 | 30 | 2017-03-18 | 1
BEEP-P143580-SH-42-G-16-FBIH |  | Purchasing and Instalation (Performance Monitoring System for measuring the heat energy usage) (for 19 buildings) - 2017. buldings (allocated) |  | G |  | SH | Post | 2017-01-15 | 0 | 2017-01-15 | 0 | 2017-01-15 | 7 | 2017-01-22 | 1 | 2017-01-23 | 3 | 2017-01-26 | 0 | 2017-01-26 | 0 | 2017-01-26 | 0 | 2017-01-26 | 30 | 2017-02-25 | 1
| A | [6 empty] | 2017-01-23 | 0 | 2017-01-23 | 0 | 2017-01-23 | 7 | 2017-01-30 | 2 | 2017-02-01 | 0 | 2017-02-01 | 0 | 2017-02-01 | 0 | 2017-02-16 | 0 | 2017-02-16 | 30 | 2017-03-18 | 1
BEEP-P143580-SH-43-G-16-FBIH |  | Purchasing of Motor Vechicle (allocated) |  | G |  | SH | Post | 2016-02-10 | 8 | 2016-02-18 | 3 | 2016-02-22 | 14 | 2016-02-22 | 1 | 2016-02-22 | 3 | - | 0 | 2016-03-07 | 0 | 2016-03-08 | 0 | 2016-03-08 | 30 | 2016-04-07 | 1
| A | [6 empty] | 2016-02-10 | 8 | 2016-02-18 | 3 | 2016-02-22 | 14 | 2016-02-22 | 1 | 2016-02-22 | 3 | - | 0 | 2016-03-07 | 0 | 2016-03-08 | 0 | 2016-03-08 | 30 | 2016-04-07 | 1
BEEP-P143580-SH-44-G-17-FBIH |  | Procure and install additional equipment of seasonal pellet tank with pellet transporter from pellet tank to pellet boiler to make it easier for beneficiaries for 7 public buildings (allocated) |  | G |  | SH | Post | 2017-09-11 | 0 | 2017-09-11 | 0 | 2017-09-11 | 14 | 2017-09-25 | 1 | 2017-09-26 | 3 | 2017-09-29 | 0 | 2017-09-29 | 0 | 2017-09-29 | 0 | 2017-09-29 | 20 | 2017-10-19 | 1
BEEP-P143580-SH-45-G-17-FBIH |  | Procure and install automatic regulation system for 11 objects as follows: a. Comprehensive automatic regulation system for 5 objects; b. Room temperature sensors with programming of existing controller with goal to make correction in line with interior temperature for 6 objects. |  | G |  | SH | Post | 2017-09-11 | 0 | 2017-09-11 | 0 | 2017-09-11 | 14 | 2017-09-25 | 1 | 2017-09-26 | 3 | 2017-09-29 | 0 | 2017-09-29 | 0 | 2017-09-29 | 0 | 2017-09-29 | 20 | 2017-10-19 | 1
|  | TOTAL GOODS (Performance Monitoring System) | [24 empty] | 1
allocated
to be allocated
TOTAL COMPONENT 1 W+G
allocated
to be allocated
SUMMARY
COMPONENT 1
Consulting Services
Allocated
to be allocated
Works and Goods
Allocated
to be allocated
Total COMPONENT 1
COMPONENT 2
Allocated
to be allocated
Total COMPONENT 2
COMPONENT 3
Allocated
to be allocated
Total COMPONENT 3
GRAND TOTAL
Allocated
to be allocated
GRAND TOTAL
Formulas:
No Objection Date = [Submis- sion/ Readiness Date]+[Days Interval]
Invita- tion Date = [No Objection Date]+[Days Interval]
Invita- tion Date = [Bid- Opening Date]-[Days Interval]
Bid- Opening Date = [Invita- tion Date]+[Days Interval]
Bid- Opening Date = [Invita- tion Date]+[Days Interval]+1
Evalu- ation & Recomm. = [Bid- Opening Date]+[Days Interval]
No Objection Date + PSC = [Evalu- ation & Recomm.]+[Days Interval]
Contract Award Date = [No Objection Date + PSC]+[Days Interval]
contarct Siganture date = [Contract Award Date]+[Days Interval]
Start Date = [contarct Siganture date]+[Days Interval]
Comple- tion Date = [Start Date]+[Days Execution]